## Timeline
Chaffee Common Ground Grant Application |  |  | Attachment 2
Program or Project Budget Timeline Template
Beginning Date | Ending Date | Activity | Reponsible Person | Comments/Milestones

## Timeline Example
Chaffee Common Ground Grant Application |  |  |  | Example of a completed Timeline
Program or Project Budget Timeline Template - Example
Beginning Date | Ending Date |  | Activity | Responsible Person | Comments/Milestones
2018-02-01 | 2018-02-01 | 1 | MJP formally accepts METAB grant Funding; meet with CCDC staff to determine date, times and location of Women's mediation class. | Board; Coordinator; CCDC Commander
2018-02-01 | 2018-02-15 | 15 | Identify 3 volunteers to complete training , register for training | Coordinator | completion of training
2018-02-01 | 2018-04-19 | 78 | Conduct Men's mindfulness Program | Teachers
2018-02-01 | 2019-01-30 | 364 | Administer Pre- and Post-MSES-R Assessments for each class; conduct weekly men's and women's yoga classes | Teachers, Coordinator
2018-02-05 | 2018-02-05 | 1 | Meet with yoga teachers to set curriculum expectations; guidelines, and assessment strategies | Coordinator
2018-02-21 | 2018-05-09 | 78 | Conduct Women's Mindfulness program | Teachers | training complete
2018-03-30 | 2018-05-11 | 43 | Train 3 new facilitators | Coordinator
2018-04-15 | 2018-12-15 | 245 | Identify additional funding sources; apply for grants | Coordinator
2018-04-19 | 2018-04-25 | 7 | Evaluate Men's Mindfulness Program feedback, make adjustments as needed | Teachers, Coordinator | completion of evaluation
2018-04-26 | 2018-07-12 | 78 | Conduct M12 week Men's Mindfulness Program | Teachers
2018-05-10 | 2018-05-15 | 6 | Evaluate 1st Women's Mindfulness Program feedback, make adjustments as needed | Teachers, Coordinator
2018-05-16 | 2018-08-01 | 78 | Conduct Women's Mindfulness program | Teachers
2018-07-18 | 2018-10-12 | 87 | Conduct 12 week Men's Mindfulness Program | Teachers
2018-08-08 | 2018-10-31 | 85 | Conduct Women's Mindfulness program | Teachers
2018-10-18 | 2019-01-12 | 87 | Conduct 12 week Men's Mindfulness Program | Teachers
2018-11-07 | 2019-01-30 | 85 | Conduct Women's Mindfulness program | Teachers
2019-01-31 | 2019-01-31 | 1 | Final Evaluations complete; reports to stakeholders (funders, CCDC) | Coordinator | completion of final evaluations
2019-01-31 | 2019-01-31 | 1 | Grant Close-out | Coordinator | completion of grant
Note on B3: Author: JP